## Sheet1
Template 1: List of Projects from 2013 to date
S/No | Department | Name of The Project | Start Date | Expected date of Completion | Project Cost (Kshs) | Total Expenditure | Status
1 | ICT | Internet Connectivity to Government Offices | 2013-10-11 | 30/06/2014 | 3000 | 2500 | Complete
2 | ICT | Local Area Networks to Government Officers | 2013-10-11 | 30/06/2014 | 5500 | 0 | Complete
3 | ICT | Furnishing of HQ offices | 2013-10-11 | 30/06/2014 | 7800 | 7800 | Complete
Template 2: List of all stalled Projects
S/No | Sub County | Ward | Department | Project Description/ Location | Project Initiation Period/Start date | Project Expected End date as per the contract | Stalled Period | Project Status (% completion) | Contract sum | Payment made to date | Functionality Status | Reason (s) for Stalling
1 | Machakos | Muvuti/ Kiima Kimwe | Trade | Construction of Market shed at Kaseve | 2014-07-01 | 2015-03-12 | 7 yrs | 70% | 5000 | 1000 | Not functional | Stopped by KeNHA
2
3