## Project Types
Project Type Code | Project Type Name | Description | Typical Sector | Notes
ROAD-ACCESS | Access Road Improvement | Routine construction, grading, gravelling, drainage, and spot improvement of local access roads. | Roads and Transport | Use for ward roads, feeder roads, and market access roads.
WATER-BOREHOLE | Borehole and Water Supply | Drilling, equipping, storage, piping, and commissioning of community water supply projects. | Water and Irrigation | Use for boreholes, tanks, kiosks, and reticulation works.
ECDE-CLASSROOM | ECDE Classroom Construction | Construction and equipping of early childhood development classrooms and related facilities. | Education | Use for ECDE classrooms, sanitation blocks, and basic furniture packages.
HEALTH-FACILITY | Health Facility Upgrade | Renovation, expansion, equipping, and commissioning of dispensaries, health centres, or maternity units. | Health Services | Use where procurement needs staged facility upgrade milestones.
MARKET-SHED | Market Shed and Trading Facility | Construction or rehabilitation of market sheds, stalls, drainage, sanitation, and lighting. | Trade and Industrialization | Use for market shelters, kiosks, paving, and basic public amenities.

## Milestone Templates
Project Type Code | Project Type Name | Sequence Order | Milestone Name | Milestone Description | Unit of Measure | Target Achievement Value
ROAD-ACCESS | Access Road Improvement | 1 | Site handover and route confirmation | Confirm chainage, access constraints, scope boundaries, and site possession. | No. | 1
ROAD-ACCESS | Access Road Improvement | 2 | Bush clearing and earthworks | Clear vegetation, shape formation, open side drains, and prepare road bed. | Km | 2.5
ROAD-ACCESS | Access Road Improvement | 3 | Culverts and drainage structures | Install culverts, mitre drains, scour checks, and other drainage controls. | No. | 6
ROAD-ACCESS | Access Road Improvement | 4 | Gravelling and compaction | Place approved gravel material, spread, water, and compact to required standard. | Km | 2.5
ROAD-ACCESS | Access Road Improvement | 5 | Inspection, defects correction, and completion | Joint inspection, snag correction, measurement, and completion certificate. | No. | 1
WATER-BOREHOLE | Borehole and Water Supply | 1 | Hydrogeological survey and permits | Complete survey, siting, environmental screening, and drilling approvals. | No. | 1
WATER-BOREHOLE | Borehole and Water Supply | 2 | Borehole drilling and test pumping | Drill borehole, case, gravel pack, develop, and perform test pumping. | No. | 1
WATER-BOREHOLE | Borehole and Water Supply | 3 | Equipping and power installation | Install pump, controls, solar or grid connection, and protection works. | No. | 1
WATER-BOREHOLE | Borehole and Water Supply | 4 | Storage and distribution works | Construct tank base, install tank, pipework, kiosks, and fittings. | No. | 1
WATER-BOREHOLE | Borehole and Water Supply | 5 | Water quality testing and commissioning | Carry out quality test, disinfect, train operators, and commission system. | No. | 1
ECDE-CLASSROOM | ECDE Classroom Construction | 1 | Site handover and setting out | Confirm site, drawings, levels, and construction boundaries. | No. | 1
ECDE-CLASSROOM | ECDE Classroom Construction | 2 | Foundation and substructure works | Excavation, foundation concrete, walling below slab, and hardcore filling. | No. | 1
ECDE-CLASSROOM | ECDE Classroom Construction | 3 | Walling, roofing, and external envelope | Walling, ring beam, roof structure, covering, doors, windows, and finishes base. | No. | 1
ECDE-CLASSROOM | ECDE Classroom Construction | 4 | Finishes, fittings, and services | Plaster, floor, painting, electrical works, sanitation, furniture, and signage. | No. | 1
ECDE-CLASSROOM | ECDE Classroom Construction | 5 | Final inspection and handover | Snag list closure, completion certificate, and handover to school committee. | No. | 1
HEALTH-FACILITY | Health Facility Upgrade | 1 | Facility assessment and site handover | Confirm priority rooms, service continuity plan, drawings, and site possession. | No. | 1
HEALTH-FACILITY | Health Facility Upgrade | 2 | Civil works and structural alterations | Carry out demolitions, masonry, roofing, partitions, ramps, and core renovations. | No. | 1
HEALTH-FACILITY | Health Facility Upgrade | 3 | Mechanical, electrical, and plumbing works | Install water, drainage, electrical fittings, lighting, ventilation, and medical utility points. | No. | 1
HEALTH-FACILITY | Health Facility Upgrade | 4 | Equipment supply and installation | Supply, install, test, and label approved facility equipment. | No. | 1
HEALTH-FACILITY | Health Facility Upgrade | 5 | Testing, user training, and commissioning | Run tests, train facility staff, close defects, and commission upgraded facility. | No. | 1
MARKET-SHED | Market Shed and Trading Facility | 1 | Site confirmation and trader engagement | Confirm site boundaries, temporary relocation needs, access, and trader communication. | No. | 1
MARKET-SHED | Market Shed and Trading Facility | 2 | Foundations and structural frame | Construct foundations, columns, steel or timber frame, and core support works. | No. | 1
MARKET-SHED | Market Shed and Trading Facility | 3 | Roofing, stalls, and floor works | Install roof covering, gutters, stalls, concrete floor, paving, and access paths. | No. | 1
MARKET-SHED | Market Shed and Trading Facility | 4 | Drainage, sanitation, and lighting | Complete drainage, water points, sanitation, security lighting, and waste handling points. | No. | 1
MARKET-SHED | Market Shed and Trading Facility | 5 | Inspection, allocation support, and handover | Inspect works, correct defects, support stall mapping, and hand over facility. | No. | 1

## Sample BQ Templates
Project Type Code | Linked Milestone Name | Activity Name | Activity Description | Unit of Measure | Quantity | Unit Cost | Budget Amount | Sort Order
ROAD-ACCESS | Bush clearing and earthworks | Bush clearing and grubbing | Clear vegetation and dispose unsuitable material. | Km | 2.5 | 85000 | 212500 | 1
ROAD-ACCESS | Culverts and drainage structures | 600mm concrete culvert installation | Supply and install culvert barrels including headwalls. | No. | 6 | 120000 | 720000 | 2
ROAD-ACCESS | Gravelling and compaction | Approved gravel wearing course | Place and compact gravel to approved thickness. | Km | 2.5 | 450000 | 1125000 | 3
WATER-BOREHOLE | Borehole drilling and test pumping | Borehole drilling | Drill and case borehole to approved depth. | No. | 1 | 1850000 | 1850000 | 1
WATER-BOREHOLE | Equipping and power installation | Solar pumping system | Supply and install pump, panels, controls, and accessories. | No. | 1 | 950000 | 950000 | 2
ECDE-CLASSROOM | Walling, roofing, and external envelope | Classroom superstructure | Walling, roofing, doors, and windows. | No. | 1 | 2600000 | 2600000 | 1
ECDE-CLASSROOM | Finishes, fittings, and services | Internal and external finishes | Plastering, flooring, painting, electricals, and fittings. | No. | 1 | 900000 | 900000 | 2
HEALTH-FACILITY | Equipment supply and installation | Basic facility equipment package | Supply and install approved medical and utility equipment. | Lot | 1 | 1800000 | 1800000 | 1
MARKET-SHED | Roofing, stalls, and floor works | Market shed roof and stalls | Roof covering, stall partitions, floor slab, and paving. | Lot | 1 | 3200000 | 3200000 | 1

## Guide
Topic | Guidance
Purpose | Sample project type, milestone, and optional BQ template data for the Machakos project management system.
Project Types | One row per reusable project type/category. In the system this maps to categoryName and description.
Milestone Templates | One row per milestone under a project type. Required fields are Project Type Code, Sequence Order, and Milestone Name.
Unit and Target | Use Unit of Measure and Target Achievement Value where the milestone has a measurable output, for example Km, No., Lot, or percentage.
Sample BQ Templates | Optional reference sheet for procurement scope lines that may be linked to milestones. Budget Amount can be Quantity x Unit Cost.
Import Note | This workbook is a sample/reference file. If an import feature is added later, keep the project type codes stable so milestones and BQ lines can map correctly.

## Lookup (hidden)
Project Type Code | Project Type Name
ROAD-ACCESS | Access Road Improvement
WATER-BOREHOLE | Borehole and Water Supply
ECDE-CLASSROOM | ECDE Classroom Construction
HEALTH-FACILITY | Health Facility Upgrade
MARKET-SHED | Market Shed and Trading Facility